myQode Distributor Portal

Fee Calculation Revamp - Implementation Plan

Confidential  |  Qode Advisors LLP  |  July 2026

Prepared for: Sanket (Tech)  |  Krish (IR)  |  Krutika (Distributor Associate)

| 2 issues identified Hardcoded split and incorrect discount pass-through causing revenue leakage | 3 fee structures Option 1 Hybrid, Option 2 Pure Performance, Option 3 Pure Fixed - all affected | 4 weeks to go-live Zoho field work, API integration, UAT, and distributor communications |
| --- | --- | --- |

IMPORTANT: Fields marked Critical under Priority must be completed before the next quarterly invoicing cycle. Zoho field work (Krish) must be finished before Sanket can begin the API integration. Do not go live without UAT sign-off across at least three distributor types.

Part 1 - Background and Problem Statement

The myQode Distributor Portal currently has two issues causing incorrect fee calculations and revenue leakage for Qode Advisors LLP. Both need to be fixed before the next quarterly invoicing cycle.

Issue 1 - Hardcoded Distributor Split

The portal uses a flat 50% distributor share assumption for every distributor, regardless of what was actually agreed. Funds India, for example, is on a 60% Flat Custom Split per their agreement, and this is already stored in Zoho CRM. That data is simply not being pulled into the portal yet, so every calculation is wrong at source.

Issue 2 - Discount Being Shared Instead of Absorbed

Some distributors are passing on fee discounts to investors at their end, charging, say, 2% when the rack rate is 2.5%. The portal currently splits the discounted fee, which means Qode ends up receiving less than its contractually agreed share. The correct treatment is that the split must always be applied on the rack rate, and any discount the distributor gives comes entirely out of their own share.

Example:

| SCENARIO | RACK RATE | CHARGED TO INVESTOR | SPLIT | QODE GETS | DISTRIBUTOR GETS |
| --- | --- | --- | --- | --- | --- |
| Correct (rack rate basis) | 2.5% | 2.0% (discounted) | 50/50 | 1.25% | 0.75% (after discount) |
| Current (wrong) | 2.5% | 2.0% (discounted) | 50/50 | 1.0% | 1.0% |

Note: The rack rate must always be the basis for the Qode-Distributor split. Any discount a distributor gives to an investor is absorbed entirely by the distributor's share. Qode's revenue is always: Rack Rate Fee x Qode Split %.

Part 2 - Fee Structures Reference

Investors choose one of three options at onboarding. Fixed fees are charged quarterly on daily average AUM. Performance fees are charged annually and subject to High Watermark where  applicable.

| PARTICULARS | OPTION 1 (HYBRID) | OPTION 2 (PURE PERFORMANCE) | OPTION 3 (PURE FIXED) |
| --- | --- | --- | --- |
| Fixed Fee | 1.50% | 0% | 2.50% |
| Performance Fee | 15% | 20% | 0% |
| Hurdle Rate | 10% | 0% | 0% |
| High Watermark | Yes | Yes | No |

Split Logic by Fee Component

The rack rate rule applies independently to each fee component. For Hybrid accounts (Option 1), the fixed fee split and performance fee split are calculated separately, each on their respective rack rates. This matters for portal display and for ensuring the correct amounts appear on distributor invoices.

Part 3 - Zoho CRM Field Requirements

All fields below need to exist in Zoho before Sanket can build the portal integration. Fields marked EXISTS are already present and need to be verified for accuracy. Fields marked ADD need to be created by Krish.

Section A - Fee Sharing Fields (Distributor Module)

| FIELD NAME (API) | DESCRIPTION | TYPE | STATUS |
| --- | --- | --- | --- |
| Revenue_Sharing_Model | Standard 50:50, Flat Custom Split, Tiered, Special Arrangement | Picklist | EXISTS |
| Base_Distributor_Share | Agreed distributor % on rack rate fees | Decimal | EXISTS |
| Effective_Revenue_Share | Computed effective share - handles tiered logic | Decimal | EXISTS |
| Tiered_Revenue_Details | AUM-based tier breakpoints where model is Tiered | Long Text | EXISTS |
| Revenue_Sharing_Notes | Free text for any special arrangements | Long Text | EXISTS |

Section B - New Fields to Add (Distributor Module)

| FIELD NAME (API) | DESCRIPTION | TYPE | STATUS |
| --- | --- | --- | --- |
| Fixed_Fee_Split_Basis | Confirm split applies on rack rate fixed fee, not discounted fee | Checkbox | ADD |
| Performance_Fee_Split_Basis | Confirm perf fee split also applies on rack rate basis | Checkbox | ADD |
| Discount_Allowed | Whether this distributor is permitted to offer fee discounts | Picklist | ADD |
| Max_Discount_Permitted | If discount is allowed, the maximum % they can pass on | Decimal | ADD |
| Qode_Fixed_Fee_Share | Auto-calculated: 100 minus Base_Distributor_Share. Read-only for portal. | Formula | ADD |
| Qode_Perf_Fee_Share | Store separately if perf fee split differs from fixed fee split | Decimal | ADD |
| Portal_Display_Name | Display name for this distributor on the portal | Text | ADD |

Section C - New Fields to Add (Investors Module)

These fields need to exist at account level so the portal can calculate fees correctly per account, independent of any discount the distributor may be passing on.

| FIELD NAME (API) | DESCRIPTION | TYPE | STATUS |
| --- | --- | --- | --- |
| Fee_Option | Option 1, Option 2, or Option 3 | Picklist | CONFIRM EXISTS |
| Rack_Rate_Fixed_Fee | Contractual rack rate fixed fee % per agreement | Decimal | ADD |
| Rack_Rate_Perf_Fee | Contractual rack rate performance fee % | Decimal | ADD |
| Rack_Rate_Hurdle | Hurdle rate applicable for this account | Decimal | ADD |
| Actual_Fee_Charged | Fee actually charged to investor - may be discounted | Decimal | ADD |
| Fee_Discount_Applied | Whether a discount was passed on to this investor | Checkbox | ADD |
| Linked_Distributor | Lookup to Distributor module record | Lookup | CONFIRM EXISTS |

Part 4 - Portal Fee Calculation Logic

This is the step-by-step logic Sanket should build into the fee engine. Each step depends on the Zoho fields in Part 3 being populated correctly first.

Step 1 - Pull from Zoho per account

- Rack_Rate_Fixed_Fee and Rack_Rate_Perf_Fee from investor record

- Actual_Fee_Charged from investor record (if a discount was applied)

- Base_Distributor_Share % from the linked distributor record

- Revenue_Sharing_Model to determine whether tiered logic applies

- Daily Average AUM from portfolio data (already working)

Step 2 - Calculate rack rate fees

- Rack Fixed Fee Amount = Daily Avg AUM x Rack_Rate_Fixed_Fee% / 4 (quarterly)

- Rack Perf Fee Amount = Gains above Hurdle x Rack_Rate_Perf_Fee% (annual, with High Watermark check for Options 1 and 2)

- Total Rack Rate Fee = Rack Fixed Fee + Rack Perf Fee

Step 3 - Apply revenue split on rack rate

- Qode Fixed Fee Share = Rack Fixed Fee Amount x (1 - Base_Distributor_Share%)

- Distributor Fixed Fee Share = Rack Fixed Fee Amount x Base_Distributor_Share%

- Same logic applies independently to the performance fee component

Step 4 - Account for discount

- Actual Fixed Fee Billed = Daily Avg AUM x Actual_Fee_Charged%

- Discount Amount = Rack Fixed Fee Amount minus Actual Fixed Fee Billed

- This discount is deducted entirely from the distributor's share, not from Qode's

- Net Distributor Payout = Distributor Fixed Fee Share minus Discount Amount

Step 5 - GST

- GST at 18% is calculated on the total rack rate fee

- Distributor invoice should reflect their net payout plus proportionate GST on their share

Note: The portal should show both Rack Rate Fee and Actual Fee Billed as separate columns so distributors can clearly see how any discount has been absorbed from their side. Qode's share column should always reflect the rack-rate-based split and should not be visible to the distributor login.

Revised Portal Table Columns

| COLUMN | WHAT IT SHOWS | VISIBLE TO DISTRIBUTOR |
| --- | --- | --- |
| Strategy / Account Code | Account identifier | Yes |
| Inception Date | Date the account went live | Yes |
| Daily Avg AUM | Average AUM for the period | Yes |
| Rack Rate Fixed Fee | Fee per agreement, before any discount | Yes |
| Rack Rate Perf Fee | Performance fee per agreement | Yes |
| Total Rack Rate Fee | Sum of the above two | Yes |
| Actual Fee Billed | What was actually charged to the investor | Yes |
| Discount Amount | Difference absorbed by distributor | Yes |
| GST (18%) | On rack rate total | Yes |
| Total (Fees + GST) | Rack rate fees plus GST | Yes |
| Distributor Split % | Pulled dynamically from Zoho CRM | Yes |
| Distributor Gross Share | Total (Fees + GST) x Distributor Split % | Yes |
| Discount Absorbed | Deducted from distributor gross share | Yes |
| Net Distributor Invoice Amount | Final amount to raise invoice for | Yes - highlighted |
| Qode Share | Internal visibility only | No - admin only |

Part 5 - Roles and Actionables

Sanket - Tech Lead

Priority: High. These need to be completed before the next quarterly invoicing cycle.

| # | ACTION | DETAIL | PRIORITY |
| --- | --- | --- | --- |
| 1 | Build Zoho CRM API integration | Pull Distributor module fields into the portal backend. Required: Base_Distributor_Share, Revenue_Sharing_Model, Effective_Revenue_Share, and linked investor rack rate fields. Krish will share the Zoho API field names once fields are confirmed. | Critical |
| 2 | Replace hardcoded 50% with dynamic split | Remove the hardcoded split from the fee calculator. Source the split % dynamically per distributor from the Zoho API response. | Critical |
| 3 | Implement rack-rate-first fee logic | Fee calculation must always start with the rack rate fee from Zoho, apply the split, then subtract any discount from the distributor's share only. Full step-by-step logic is in Part 4. | Critical |
| 4 | Add revised columns to portal table | Add Rack Rate Fee, Actual Fee Billed, Discount Amount, and Net Distributor Invoice Amount columns. Full column spec is in Part 4. | High |
| 5 | Handle tiered revenue model | For distributors on the Tiered model: pull AUM breakpoints from Zoho and apply the correct split tier per account. Test with at least one tiered distributor record before going live. | Medium |
| 6 | Separate Fixed vs Performance fee display | For Option 1 (Hybrid) accounts, show fixed fee and performance fee split separately. Confirm with Krish whether the perf fee split % ever differs from the fixed fee split % for any distributor. | Medium |
| 7 | Admin-only Qode share view | Add an internal admin view showing Qode's split alongside the distributor split. Not visible under distributor logins. | Low |
| 8 | UAT with Krish before go-live | Run test cases across at least three distributor types (Standard 50:50, 60% Custom, Tiered) and all three fee options before deploying to production. | Critical |

Krish - Investor Relations

Priority: High. Zoho fields must be ready before Sanket can start the integration.

| # | ACTION | DETAIL | PRIORITY |
| --- | --- | --- | --- |
| 1 | Audit all distributor records for split accuracy | Go through every active Funded distributor in Zoho and verify that Base_Distributor_Share % matches what was signed. Fix any records that are wrong or blank. | Critical |
| 2 | Create new fields in Distributor module | Add the seven fields listed in Section B of Part 3 using the suggested API names. Mark as mandatory where appropriate. | High |
| 3 | Create investor-level rack rate fields | Add Rack_Rate_Fixed_Fee, Rack_Rate_Perf_Fee, Rack_Rate_Hurdle, Actual_Fee_Charged, and Fee_Discount_Applied to the Investors module. | Critical |
| 4 | Backfill rack rate fields for all live accounts | For every investor account linked to a distributor, fill in the rack rate fields based on the signed PMS agreement or onboarding form. | Critical |
| 5 | Confirm Fee_Option picklist exists | Check that Option 1, Option 2, Option 3 is captured at account level in Zoho. If not, add the picklist and backfill. | High |
| 6 | Document distributors giving discounts | Identify which distributors are currently passing on fee discounts. Populate Discount_Allowed and Max_Discount_Permitted in Zoho for each. | High |
| 7 | Share API field names with Sanket | Once all fields are created and populated, export the Zoho API field name list from Field Manager and share with Sanket for portal backend mapping. | Critical |
| 8 | UAT sign-off | Run test scenarios in staging before go-live. Verify Funds India (60% split, potential discount) and at least one Standard 50:50 distributor render correctly. | Critical |

Krutika - Distributor Associate

Priority: Medium. Operational and communication tasks to run alongside the tech build.

| # | ACTION | DETAIL | PRIORITY |
| --- | --- | --- | --- |
| 1 | Collect signed fee agreements for all active distributors | Pull the signed PMS agreement or fee schedule for every active distributor. Confirm the rack rate and agreed distributor split % and share with Krish for Zoho update. | Critical |
| 2 | Flag distributors giving fee discounts | Identify distributors who are currently charging investors less than the rack rate. Document which clients, what rate was charged, and what the rack rate should have been. Share with Krish. | High |
| 3 | Communicate portal update to distributors | Once the portal is updated, send a clear note to all distributors explaining that split % is now pulled from their agreement, and any discount they give comes out of their share. | Medium |
| 4 | Update invoicing guidance for distributors | Revise the invoicing guidance to clarify: invoice for the Net Distributor Invoice Amount shown on the portal, and that the portal now shows rack rate fee separately from the net billed fee. | Medium |
| 5 | Add fee data to new distributor onboarding checklist | Add a step covering: Revenue Sharing Model, Distributor Split %, whether discount is allowed, and max discount %. This must be entered in Zoho before the portal goes live for any new distributor. | Medium |

Part 6 - Implementation Timeline

Four weeks to go-live, assuming Zoho field work and agreement collection start in Week 1 in parallel.

| WEEK | OWNER | MILESTONE |
| --- | --- | --- |
| Week 1 | Krish | Audit all distributor split % in Zoho, create new fields (Sections B and C of Part 3), share field API names with Sanket |
| Week 1 | Krutika | Collect signed agreements for all active distributors, flag discount cases to Krish |
| Week 2 | Sanket | Build Zoho API integration, replace hardcoded split, implement rack-rate-first fee logic |
| Week 2 | Krish | Backfill rack rate and discount fields for all live investor accounts |
| Week 3 | Sanket | Add revised table columns, admin view, handle tiered model, deploy to staging |
| Week 3 | Krish + Sanket | UAT: test Funds India (60% custom split), one Standard 50:50 distributor, and at least one Option 1 Hybrid fee account |
| Week 4 | All | Go-live, Krutika communicates changes to distributors and updates invoicing SOP |

Part 7 - Open Questions

These need to be resolved before Sanket can finalise the fee engine. Krish to get answers from Gaurav and Rishabh where needed.

- Does the performance fee split % ever differ from the fixed fee split % for any distributor, or is it always the same?

- For Tiered distributors: are AUM tiers calculated on the individual investor account AUM, or on the distributor's total book AUM with Qode?

- Is there a requirement for an admin login showing Qode's share on the portal, or will that always be tracked separately in Zoho?

- Are there any distributors on a Special Arrangement model, and if so, how should those be handled in the portal calculation?

- For Option 2 (Pure Performance): should the portal show a zero row for fixed fee, or suppress the fixed fee column entirely for those accounts?

- GST applicability: does it apply on the full rack rate fee, or only on the actual fee billed to the investor?

Qode Advisors LLP  |  Confidential  |  July 2026